POKER DREAM

Business Proposal

Version: 2.0

Date: 5 December 2025

Validity: 30 days (until 5 January 2026)

Table of Contents

1. Executive Summary

2. Goals & Outcomes

3. What You Get

4. Project Timeline (12 Weeks)

5. Capacity Fit

6. Your Responsibilities

7. Maintenance & Support

8. Pricing & Payment

9. Data & Privacy

10. Acceptance & Next Steps

1. Executive Summary

Poker Dream is an innovative mobile application designed specifically for poker lovers in Malaysia and around the world. The app offers a unique combination of tournament management, poker news, and engaging video content all in one platform.

At a Glance

| Item | Details |
| --- | --- |
| Delivery | Fully functional iOS & Android apps; Admin dashboard |
| Timeline | 12 weeks from kickoff |
| Ownership | You own all source code |
| Support | 30-day post-launch warranty included |

2. Goals & Outcomes

Our Vision

• One-stop destination: Your users can discover upcoming tournaments, watch highlight reels, and stay current with news—all within a single, polished mobile experience.

• Simple management: A dedicated admin panel lets your team manage tournaments, articles, and videos without technical help.

• Scalable platform: The architecture is built to grow with your business, supporting future feature additions seamlessly.

Who Benefits

| Audience | Key Benefits |
| --- | --- |
| Players | Browse tournaments, view schedules & buy-ins, register interest |
| Fans | Watch highlight videos, read poker news |
| Organizers | Manage tournament info, publish news, maintain video library |

3. What You Get

A) Mobile Application (iOS & Android)

A native-feel app that works on both platforms:

Home Screen

• Highlight video carousel with auto-play previews

• Quick-access grid for Events, News, Videos, and more

• Latest news headlines

Tournaments / Series

• List of upcoming, live, and completed events

• Search, filter by date range, buy-in, game type

• Detail pages with description, schedule, prize pool

News

• Article feed sorted by recency or category

• Full article reader with images, author info

Videos

• Video gallery with thumbnails and durations

• In-app playback (or YouTube redirect)

User Account

• Email/password authentication (email verification)

• Profile screen with avatar and display name

B) Admin Dashboard (Web)

A secure management console for your team:

Tournament Management

• Create / edit / delete tournaments

• Set dates, buy-ins, guarantee, blind structures

• Toggle visibility, mark featured events

News Management

• Rich-text editor with image uploads

• Assign categories, authors

• Schedule or instant publish

Video Management

• Upload directly or paste YouTube/external links

• Auto-extract thumbnail and duration

• Sort videos into playlists

User Management

• View registered users, reset passwords

• Assign admin or moderator roles

C) Backend & Infrastructure

| Component | Details |
| --- | --- |
| API Server | Node.js / Express, secured with JWT |
| Database | PostgreSQL (or MySQL—your choice) |
| Media | Cloudinary for images/videos |
| Email | SendGrid for transactional emails |

Everything is deployed on your cloud account for full ownership.

4. Project Timeline (12 Weeks)

| Stage | Duration | Key Outcomes |
| --- | --- | --- |
| Discovery & Setup | Weeks 1-2 | Brand guidelines locked, cloud accounts provisioned, CI/CD ready |
| Backend Build | Weeks 3-5 | API endpoints for tournaments, news, videos, auth |
| Admin Dashboard | Weeks 6-7 | All CRUD screens, media uploads, role permissions |
| Mobile App | Weeks 8-11 | iOS & Android builds, navigation, API integration |
| Testing & Launch | Week 12 | Beta testing, bug fixes, App Store / Play Store submission |

Our target is to submit to the app stores by Week 12, subject to platform review times.

Communication & Reporting

• Simple weekly progress report

• Short demo every two weeks

• Transparent issue tracking with real-time access

5. Capacity Fit

We're confident we can deliver a high-quality poker platform because:

| Experience | Details |
| --- | --- |
| API Design | We have built REST APIs serving thousands of concurrent users |
| Mobile | Our team has launched 10+ apps on iOS and Android |
| Admin Panels | We regularly build dashboards with Next.js / React |
| Security | JWT authentication, role-based access, encrypted passwords |

6. Your Responsibilities

Simple Checklist

To ensure smooth delivery, we need you to:

• Provide brand assets (logo, fonts, color palette)

• Approve designs and key screens within 3 business days where possible

• Supply sample content (tournaments, articles, videos) for testing

• Test builds during the beta phase and share feedback

• Nominate a point-of-contact for weekly reviews

Timely Feedback Required

This timeline requires your feedback within 3 business days on all deliverables. Delays in approval will extend the project timeline accordingly.

7. Maintenance & Support

Once launched, we offer two support tiers:

Option A: Care+ 24/7

| Feature | Details |
| --- | --- |
| Monthly Fee | RM 20,000/month |
| Availability | 7 days a week, including public holidays |
| Response | Critical issues within 2 hours, others within 8 hours |
| Event Days | Up to 4 high-priority event days per month |
| Improvements | 10 hours of minor enhancements / month |

Option B: Care Standard

| Feature | Details |
| --- | --- |
| Monthly Fee | RM 11,000/month |
| Availability | Monday – Friday, 9am – 6pm |
| Response | Critical issues within 4 hours, others within 24 hours |
| Event Days | Up to 1 high-priority event day per month |
| Improvements | 4 hours of minor enhancements / month |

Both plans include hosting monitoring, security patches, and routine backups.

8. Pricing & Payment

Investment Summary

| Item | Amount |
| --- | --- |
| Total Development Fee | RM 250,000 (one-time) |
| Monthly Support | RM 11,000 – RM 20,000 depending on option |

Payment Milestones

| Milestone | Timing | Amount | Percentage |
| --- | --- | --- | --- |
| Contract Signing | Upon signing | RM 62,500 | 25% |
| Backend Complete | Week 5 | RM 75,000 | 30% |
| Admin + Mobile Alpha | Week 9 | RM 75,000 | 30% |
| Final Delivery | Week 12 | RM 37,500 | 15% |

What's Included

✓ Design & build of mobile app (iOS + Android)

✓ Backend API development

✓ Admin dashboard

✓ Cloudinary & SendGrid integration

✓ App Store and Play Store submission assistance

✓ 4 hours of stakeholder training

✓ 30-day post-launch warranty

What's NOT Included

✗ Apple Developer & Google Play annual fees

✗ Third-party service subscriptions after free-tier limits

✗ Content creation (articles, videos)

✗ Marketing or ASO services

Growth & Usage-Based Costs

As your user base grows, third-party provider charges (cloud compute, media storage, email/push sends) may increase. We will:

• Enable spend alerts and budgets in your accounts

• Provide a simple monthly forecast

• Optimize caching/CDN to minimize costs

9. Data & Privacy

Our Commitment

• All user data is encrypted in transit and at rest

• Passwords are hashed using industry-standard algorithms

• Data is stored on servers you own; we do not retain copies

• You can export or delete all data at any time

• Local legal compliance (PDPA, GDPR) remains with you

10. Acceptance & Next Steps

How to Get Started

Step 1: Sign this proposal and pay the first milestone (25%)

Step 2: Kickoff call (1 hour) to confirm brand assets, timelines, and communication channels

Step 3: We begin work within 5 business days of kickoff

Signatures

Client

Name: __________________________________________________

Title: __________________________________________________

Signature: __________________________________________________

Date: __________________________________________________

Service Provider

Name: __________________________________________________

Title: __________________________________________________

Signature: __________________________________________________

Date: __________________________________________________

This proposal is confidential and valid for 30 days.

Thank you for considering Poker Dream.