BUSINESS PROPOSAL

Poker Dream Ecosystem

3-Phase Development Approach

"Your Poker Community" + "Track. Analyze. Improve."

Prepared for: [Client Name]

Prepared by: [Your Company Name]

Date: November 27, 2024

Valid Until: December 27, 2024

Table of Contents

No table of contents entries found.

EXECUTIVE SUMMARY

We are pleased to present this proposal for the development of the Poker Dream Ecosystem - a comprehensive two-app mobile platform designed to serve the global poker community.

The Ecosystem

| App | Tagline | Description |
| --- | --- | --- |
| Poker Dream Community | "Your Poker Community" | The centralized hub for poker news, events, and social interaction |
| Poker Dream Bankroll | "Track. Analyze. Improve." | Professional-grade poker performance tracking application |

Development Approach

This proposal outlines a 3-phase development approach that prioritizes the Community platform first, followed by enhancements and cross-app integration, and finally the Bankroll tracking application.

| Phase | Focus | Duration | Investment |
| --- | --- | --- | --- |
| Phase 1 | Community MVP + Admin Panel v1 | 18 weeks | RM 409,050 |
| Phase 2 | Community Enhancement + SSO | 10 weeks | RM 192,375 |
| Phase 3 | Bankroll App + Admin Panel v3 | 14 weeks | RM 334,125 |
| TOTAL | Complete Poker Dream Ecosystem | 42 weeks | RM 935,550 |

PROJECT SCOPE

App 1: Poker Dream Community

"Your Poker Community" - The centralized hub for poker news, events, and social interaction

| Module | Features |
| --- | --- |
| Home Feed | Aggregated news from poker sources, Video highlights carousel, Trending content, Command grid navigation |
| Events & Calendar | Tournament series listings (WSOP, WPT, EPT, etc.), Event calendar with filters, Real-time results tracking, Filter by status/location/date |
| Live Streams | YouTube/Twitch/Facebook stream aggregation, Live indicator badges, Upcoming streams schedule, Stream notifications |
| Social Feed | User posts with media (photos, videos), Likes/Comments/Shares, Stories feature, Follow system, Player profiles |
| Chat System | Public chat rooms by topic, Private group chats, Direct messages (DMs), Event-specific chat lounges |
| Leaderboard | Player rankings by Earnings/ROI/Cashes, Global and regional views, Timeframe filters (weekly, monthly, yearly) |
| Notifications | Push notifications, Event reminders, Follow updates, Breaking news alerts |
| Multi-Language | English and Chinese (Simplified & Traditional) localization, Language selection in settings |
| User System | Email & social login (Google, Apple, Facebook), Profile management, Premium subscription, Settings & preferences |

App 2: Poker Dream Bankroll

"Track. Analyze. Improve." - Professional-grade poker performance tracking application

| Module | Features |
| --- | --- |
| Dashboard | Balance overview with charts, Quick stats (ROI, Win Rate, ITM%), Recent sessions list, Performance trend graphs |
| Bankroll Management | Balance tracking, Deposits/Withdrawals logging, Transaction history, Financial goals setting & tracking |
| Session Logging | Cash game logging (stakes, duration, venue, profit/loss), Tournament logging (buy-in, position, payout), Quick entry (<90 seconds), Notes & tags |
| Statistics & Analytics | ROI calculation, Win rate tracking, ITM% for tournaments, Hourly rate analysis, Filters by venue/stakes/game type/date, Trend analysis |
| Poker Tools | ICM Calculator (Independent Chip Model), Equity Calculator (hand vs hand), Hand Ranges builder (visual tool) |
| Data Export | CSV export for spreadsheets, PDF reports (for tax purposes), Date range selection, Custom report generation |
| Multi-Language | English and Chinese (Simplified & Traditional) - shared localization with Community app |
| User System | Email & social login (SSO with Community app), Profile management, Cloud sync across devices, Settings & preferences |

Admin Panel (Web Dashboard)

Comprehensive web-based administration panel for managing both applications

| Module | Features |
| --- | --- |
| User Management | View all users with search & filter, User details & activity history, Roles & permissions management, Account status (active/suspended/banned), Bulk actions |
| Content Management | News articles CRUD (Create, Read, Update, Delete), Events management, Featured content curation, Announcements & banners, Media library |
| Moderation Tools | Chat moderation queue, Report handling workflow, Content flagging system, User warnings & bans, Automated moderation rules |
| Analytics Dashboard | User metrics (DAU/MAU/retention), Engagement statistics, Revenue tracking, Feature usage analytics, Custom date ranges |
| Subscription Management | Premium user management, Subscription status tracking, Revenue reports, Renewal & cancellation management |
| System Settings | App configuration, Feature toggles (enable/disable features), Push notification settings, Maintenance mode, API management |

Cross-App Integration

• Single Sign-On (SSO): Unified user accounts - login once, access both apps seamlessly

• Profile Sync: Optional synchronization of profile data between apps

• Share to Feed: Share Bankroll results/achievements to Community social feed

• Cross-Promotion: In-app promotion and deep linking between the two apps

• Unified Analytics: Combined user insights and behavior tracking across both platforms

PHASE 1

Poker Dream Community MVP

Duration: 18 weeks  |  Investment: RM 409,050

Objective: Launch the core community platform with essential features to attract and engage poker enthusiasts.

Timeline Breakdown

| Component | Duration | Description |
| --- | --- | --- |
| Discovery & Design | 4 weeks | Requirements gathering, UI/UX design, wireframes, prototypes, technical architecture |
| Infrastructure & DevOps Setup | 2 weeks | Dev/Staging/Prod environments, CI/CD pipelines, Supabase setup, Firebase configuration |
| App Development | 8 weeks | Core community features implementation |
| R&D & Integration Testing | 1 week | Third-party integration testing (Supabase Realtime, Push, Social Login) |
| Admin Panel v1 | 2 weeks | User management, content CMS, basic moderation, analytics dashboard |
| QA & Launch | 1 week | Testing, bug fixes, App Store submission (iOS & Android) |

Deliverables - Poker Dream Community App

The following modules and features will be delivered:

| Module | Features Included |
| --- | --- |
| Home Feed | Aggregated news from poker sources, Video highlights carousel, Trending content, Command grid navigation |
| Events & Calendar | Tournament series listings (WSOP, WPT, EPT, etc.), Event calendar with filters, Real-time results tracking, Filter by status/location/date |
| Live Streams | YouTube/Twitch/Facebook stream aggregation, Live indicator badges, Upcoming streams schedule, Stream notifications |
| Social Feed | User posts with media (photos, videos), Likes/Comments/Shares, Stories feature, Follow system, Player profiles |
| Chat System | Public chat rooms by topic, Private group chats, Direct messages (DMs), Event-specific chat lounges |
| Notifications | Push notifications, Event reminders, Follow updates, Breaking news alerts |
| Multi-Language | English and Chinese (Simplified & Traditional) localization, Language selection in settings |
| User System | Email & social login (Google, Apple, Facebook), Profile management, Settings & preferences |

Deliverables - Admin Panel v1

| Module | Features Included |
| --- | --- |
| User Management | View all users with search & filter, User details & activity history, Account status management |
| Content Management | News articles CRUD, Events management, Featured content curation, Announcements |
| Moderation Tools | Chat moderation queue, Report handling, Content flagging system, User warnings & bans |
| Analytics Dashboard | User metrics (DAU/MAU), Engagement statistics, Basic reporting |

Additional Deliverables

| Deliverable | Description |
| --- | --- |
| Design System | Figma files, component library, brand guidelines |
| Technical Documentation | Architecture docs, API documentation, deployment guides |
| DevOps Infrastructure | CI/CD pipelines, Dev/Staging/Prod environments, automated deployments |
| App Store Listings | Published on Apple App Store and Google Play Store |

Phase 1 Investment

| Component | Investment |
| --- | --- |
| Discovery & Design | RM 48,600 |
| Infrastructure & DevOps Setup | RM 32,400 |
| Community MVP Development | RM 251,100 |
| R&D & Integration Testing | RM 6,075 |
| Admin Panel v1 | RM 40,500 |
| QA & Launch | RM 6,075 |
| Project Management | RM 6,075 |
| Total Phase 1 | RM 409,050 |

PHASE 2

Poker Dream Community Enhancement

Duration: 10 weeks  |  Investment: RM 192,375

Objective: Add premium features, monetization, and prepare infrastructure for Bankroll app integration.

Timeline Breakdown

| Component | Duration | Description |
| --- | --- | --- |
| Premium Features | 4 weeks | Subscription system, leaderboard, player profiles, exclusive content |
| R&D & Integration Testing | 1 week | RevenueCat payment integration, In-App Purchase testing |
| Cross-App Integration | 2 weeks | SSO infrastructure, shared APIs, profile sync |
| Admin Panel v2 | 1 week | Premium user management, revenue analytics, advanced moderation |
| QA & Deployment | 2 weeks | Testing, payment flow validation, App Store update |

Deliverables - Premium Features

The following premium features will be added to the Community app:

| Feature | Details |
| --- | --- |
| Premium Subscription | In-app purchases via RevenueCat, Monthly/Yearly plans, Ad-free experience, Restore purchases |
| Leaderboard | Player rankings by Earnings/ROI/Cashes, Global and regional views, Timeframe filters (weekly, monthly, yearly, all-time) |
| Enhanced Player Profiles | Public stats display, Achievement badges, Verified player status, Profile customization |
| Exclusive Content | Premium-only articles, Advanced event insights, Early access to features |
| Priority Support | Faster response times, Dedicated support channel for premium users |

Deliverables - Cross-App Integration

| Component | Details |
| --- | --- |
| Single Sign-On (SSO) | Unified authentication system, Login once access both apps, Token-based session management |
| Shared User Profiles | Optional profile sync between apps, Unified avatar and display name, Privacy controls |
| Share to Feed API | API endpoint for Bankroll app to post achievements, Result sharing with privacy options |
| Deep Linking | Cross-app navigation, Universal links setup (iOS), App links setup (Android) |

Deliverables - Admin Panel v2

| Module | Features Included |
| --- | --- |
| Premium Management | Premium user list, Subscription status tracking, Manual subscription grants |
| Revenue Analytics | Subscription revenue reports, Conversion metrics, Churn analysis |
| Advanced Moderation | Automated moderation rules, Bulk moderation actions, Appeal handling workflow |
| Leaderboard Management | Verify player identities, Adjust rankings, Feature players |

Phase 2 Investment

| Component | Investment |
| --- | --- |
| Premium Features Development | RM 97,200 |
| R&D & Integration Testing | RM 6,075 |
| Cross-App Integration | RM 48,600 |
| Admin Panel v2 | RM 10,125 |
| QA & Deployment | RM 8,100 |
| Project Management | RM 6,075 |
| Total Phase 2 | RM 192,375 |

PHASE 3

Poker Dream Bankroll

Duration: 14 weeks  |  Investment: RM 334,125

Objective: Launch the professional poker tracking application with seamless integration to the Community app.

Timeline Breakdown

| Component | Duration | Description |
| --- | --- | --- |
| Discovery & Design | 2 weeks | Bankroll-specific UI/UX design, leveraging existing design system |
| DevOps & Environment | 1 week | Bankroll app CI/CD pipeline, database schema, SSO integration |
| MVP Development | 6 weeks | Dashboard, bankroll management, session logging, statistics |
| R&D & Integration Testing | 1 week | Calculator tools testing, export functions, SSO flow |
| Pro Features | 2 weeks | ICM calculator, equity calculator, hand ranges, data export |
| Admin Panel v3 | 1 week | Bankroll analytics, subscription management, cross-app insights |
| QA & Launch | 1 week | Testing, App Store submission (iOS & Android) |

Deliverables - Poker Dream Bankroll App

The following modules and features will be delivered:

| Module | Features Included |
| --- | --- |
| Dashboard | Balance overview with charts, Quick stats (ROI, Win Rate, ITM%), Recent sessions list, Performance trend graphs |
| Bankroll Management | Balance tracking, Deposits/Withdrawals logging, Transaction history, Financial goals setting & tracking |
| Session Logging | Cash game logging (stakes, duration, venue, profit/loss), Tournament logging (buy-in, position, payout), Quick entry (<90 seconds), Notes & tags |
| Statistics & Analytics | ROI calculation, Win rate tracking, ITM% for tournaments, Hourly rate analysis, Filters by venue/stakes/game type/date, Trend analysis |
| Multi-Language | English and Chinese (Simplified & Traditional) - shared localization with Community app |
| User System | SSO with Community app, Profile management, Cloud sync across devices, Settings & preferences |

Deliverables - Pro Features

| Feature | Details |
| --- | --- |
| ICM Calculator | Independent Chip Model calculator, Multi-player scenarios, Deal equity calculations |
| Equity Calculator | Hand vs hand equity, Hand vs range calculations, Board texture analysis |
| Hand Ranges Builder | Visual range editor, Pre-defined ranges, Custom range creation and saving |
| CSV Export | Export all sessions to CSV, Custom date range selection, Compatible with Excel/Google Sheets |
| PDF Reports | Professional reports for tax purposes, Summary statistics, Itemized session history |

Deliverables - Cross-App Features

| Feature | Details |
| --- | --- |
| SSO Integration | Seamless login with Community app credentials, Shared authentication tokens |
| Share to Community | Share session results to Community social feed, Share achievements/milestones, Privacy controls for what to share |
| Profile Sync | Sync display name and avatar from Community, Optional public stats display |

Deliverables - Admin Panel v3

| Module | Features Included |
| --- | --- |
| Bankroll Analytics | User session statistics, Popular venues/stakes, Usage patterns |
| Subscription Management | Pro subscription status, Revenue tracking for Bankroll app |
| Cross-App Insights | Unified user analytics, Cross-app engagement metrics, Conversion tracking |
| System Settings | Calculator configurations, Export templates, Feature toggles |

Phase 3 Investment

| Component | Investment |
| --- | --- |
| Discovery & Design | RM 6,075 |
| DevOps & Environment Setup | RM 8,100 |
| Bankroll MVP Development | RM 170,100 |
| R&D & Integration Testing | RM 6,075 |
| Bankroll Pro Features | RM 36,450 |
| Admin Panel v3 | RM 10,125 |
| QA & Launch | RM 10,125 |
| Project Management | RM 8,100 |
| Total Phase 3 | RM 334,125 |

INVESTMENT SUMMARY

Total Project Investment

| Phase | Duration | Investment |
| --- | --- | --- |
| Phase 1: Community MVP | 18 weeks | RM 409,050 |
| Phase 2: Community Enhancement | 10 weeks | RM 192,375 |
| Phase 3: Bankroll App | 14 weeks | RM 334,125 |
| TOTAL | 42 weeks (~10.5 months) | RM 935,550 |

Cost Breakdown by Category

| Category | Phase 1 | Phase 2 | Phase 3 | Total |
| --- | --- | --- | --- | --- |
| Discovery & Design | RM 48,600 | - | RM 6,075 | RM 36,450 |
| DevOps & Infrastructure | RM 32,400 | - | RM 8,100 | RM 48,600 |
| App Development | RM 251,100 | RM 97,200 | RM 170,100 | RM 518,400 |
| R&D & Integration Testing | RM 6,075 | RM 6,075 | RM 6,075 | RM 36,450 |
| Cross-App Integration | - | RM 48,600 | - | RM 48,600 |
| Pro Features | - | - | RM 36,450 | RM 36,450 |
| Admin Panel | RM 40,500 | RM 10,125 | RM 10,125 | RM 81,000 |
| QA & Launch | RM 6,075 | RM 8,100 | RM 10,125 | RM 30,375 |
| Project Management | RM 6,075 | RM 6,075 | RM 8,100 | RM 26,325 |
| Total | RM 409,050 | RM 192,375 | RM 334,125 | RM 935,550 |

Payment Schedule

| Milestone | Percentage | Amount |
| --- | --- | --- |
| Contract Signing | 30% | RM 280,665 |
| Phase 1 Completion | 25% | RM 233,888 |
| Phase 2 Completion | 25% | RM 233,888 |
| Phase 3 Completion | 20% | RM 187,110 |
| TOTAL | 100% | RM 935,550 |

POST-LAUNCH SUPPORT PACKAGES

After each phase launch, we offer ongoing support packages to ensure your applications remain stable, secure, and up-to-date:

| Package | Monthly Investment | Includes |
| --- | --- | --- |
| Essential | RM 11,000/month | Bug fixes, security patches, minor updates, 8 hours support |
| Growth | RM 20,000/month | Essential + feature enhancements, performance optimization, 20 hours support |
| Enterprise | RM 35,000/month | Growth + dedicated developer, priority support, 40 hours support, SLA |

What's Included in All Support Packages:

✓ Bug fixes and issue resolution

✓ Security updates and patches

✓ OS compatibility updates (iOS/Android)

✓ App Store compliance maintenance

✓ Server monitoring and uptime management

✓ Technical support via email/chat

✓ Monthly status reports

*Minimum 3-month commitment required for all support packages.

*Recommended: Growth package for active feature development and optimization.

TERMS & CONDITIONS

Payment Terms

Net 15 days from invoice date. Late payments may incur a 2% monthly interest charge.

Milestone Acceptance

5 business days review period for each milestone. Acceptance is implied if no feedback is received within the review period.

Change Requests

Any changes to the agreed scope will be handled via a formal change order process. Additional costs and timeline adjustments will be quoted separately.

Intellectual Property

Full IP ownership transfers to the client upon final payment. Source code, design files, and all assets become client property.

Confidentiality

A Non-Disclosure Agreement (NDA) is included with the contract. Both parties agree to keep project details confidential.

Warranty

90-day bug fix warranty post-launch for each phase. Covers defects in the delivered functionality as per agreed specifications.

Third-Party Services

Costs for third-party services (app store fees, cloud hosting, analytics tools) are not included and are the client's responsibility.

Project Cancellation

If the project is cancelled, payment is due for all completed work and work in progress up to the cancellation date.

Communication

Weekly progress updates via video call. Day-to-day communication via Slack or agreed platform.

Timeline

Timelines are estimates based on current scope. Delays caused by client feedback or scope changes may extend the timeline.

This proposal is confidential and intended solely for the named recipient.

Pricing is valid for 30 days from the proposal date.

Prepared with confidence. Ready to build the home for poker.